## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Digital College>
SB1/US1 | As a Student I want discussed all about of project with my team | SB1/US1/T1 | our team member desided that on which platform we are going to implement our project | AL+BK+HJ | 2022-08-12 | 2022-09-22
|  | SB1/US1/T2 | A discussion were impactfull and all the eveluation part where identified by each one of us | AL+BK+HJ | 2022-09-24 | 2022-09-29
|  | SB1/US1/T3 | install the process regarding to this project | AL+BK+HJ | 2022-09-30 | 2022-09-30
|  | SB1/US1/T4 | Start working on Sign Language recognization system | AL+BK+HJ | 2022-10-01 | 2023-02-17
|  | SB1/US1/T5 | Install firstly Anaconda and Pycham IDE | BK | 2022-10-03 | 2022-10-03
|  | SB1/US1/T6 | Install Dev C++/C code editor And QTsdk | AL+HJ+BK | 2022-10-05 | 2022-10-05
SB1/US2 | As a Student I want discussed all about of project with my team | SB1/US2/T1 | Improved knowledge Regarding to this project firstly | AL+BK+HJ | 2022-10-10 | 2022-10-22
|  | SB1/US2/T2 | Discuss Among Other team member | AL+BK+HJ | 2022-10-25 | 2022-10-25
|  | SB1/US2/T3 | Finally working start in the project module Cnn model building | BK | 2022-11-01 | 2022-12-03
|  | SB1/US2/T4 | Creation of CNN architecture our first priority | BK | 2022-11-02 | 2022-12-03
|  | SB1/US2/T5 | view my result | BK | 2022-11-04 | 2022-11-04
SB1/US3 | we discused all rules of application working and library working | SB1/US3/T1 | Include The basic requirement like Python version 3 for code purpose | BK | 2022-11-05 | 2022-11-05
|  | SB1/US3/T2 | Include The basic requirement like Tensorflow for design the neural network arcitecture | BK | 2022-11-06 | 2022-11-06
|  | SB1/US3/T3 | Include The basic requirement like PIL library for image | BK | 2022-11-07 | 2022-11-07
|  | SB1/US3/T4 | Include The basic requirement like Keras for performing the task of image preprocessing | BK | 2022-11-07 | 2022-11-07
SB1/US6 | completed all the process of CNN training | SB2/D1/T1 | Include The basic requirement like Matplotlib library for image related operation and graph architectutre | BK+HJ | 2022-11-08 | 2022-11-08
|  |  | Creating the dataset for sign language classification | BK+HJ | 2022-11-13 | 2022-11-14
|  |  | Calculate threshold value | BK | 2022-11-15 | 2022-11-15
|  |  | Flipping the frame to prevent inverted image of captured frame | BK+AL | 2022-11-16 | 2022-11-16
|  |  | Display the threshold image | HJ | 2022-11-16 | 2022-11-16
SB1/US7 | completed all process of Data set creation by apply training | SB2/D1/T1 | Display the frame with segmented handed | BK | 2022-11-17 | 2022-11-17
|  | SB2/D1/T2 | Releasing the camera | AL | 2022-11-20 | 2022-11-20
|  | SB2/D1/T3 | Training CNN | BK | 2022-11-21 | 2022-11-21
|  | SB2/D1/T4 | Improved my performance and find best solution | BK | 2022-11-22 | 2022-11-22
SB1/US27 | Model Compilation | SB2/D1/T1 | Include The basic requirement like Python version 3 for code purpose | BK | 2022-11-23 | 2022-11-23
|  | SB2/D1/T2 | Predict the gesture | BK | 2022-11-24 | 2022-11-24
|  | SB2/D1/T3 | Release the camera | BK | 2022-11-24 | 2022-11-24
|  | SB2/D1/T4 | Package binding | BK | 2022-11-26 | 2022-11-26
|  | SB2/D1/T5 | Analysis of model archictecture in img view | BK | 2022-11-27 | 2022-11-27
SB1/US27 | start work on Gesture GUI interface | SB2/D1/T1 | Start learning about the GUI creation in python using PYqt5/qt6 | AL | 2022-11-08 | 2022-11-17
|  | SB2/D1/T2 | Start learning about the GUI creation in Qt sdk toolkit | AL | 2022-11-18 | 2022-11-24
|  | SB2/D1/T3 | Start working on creation of Gesture interface and create gesture.ui file | AL | 2022-11-25 | 2022-12-02
|  | SB2/D1/T4 | Analysis of xml archictecture in grid view | AL | 2022-12-04 | 2022-12-04
SB1/US150 | start work on dash GUI interface | SB2/D1/T1 | Start learning about the GUI creation in python using PYqt5/qt6 | HJ | 2022-11-08 | 2022-11-17
|  | SB2/D1/T2 | Start learning about the GUI creation in Qt sdk toolkit | HJ | 2022-11-18 | 2022-11-24
|  | SB2/D1/T3 | Start working on creation of Gesture interface and create dash.ui file | HJ | 2022-11-25 | 2022-12-06
|  | SB2/D1/T4 | Analysis of xml archictecture in grid view | HJ | 2022-12-07 | 2022-12-07
SB1/US28 | GUI integration and testing | SB2/D1/T1 | Convert the dash.ui file into py extension for find relation b/w py component | BK+HJ+AL | 2022-12-08 | 2022-12-08
|  | SB2/D1/T2 | Convert the gest.ui file into py extension for find relation b/w py component | BK+HJ+AL | 2022-12-09 | 2022-12-09
|  | SB2/D1/T3 | The project contains multiple files ; each file is discussed separately | BK+HJ+AL | 2022-12-12 | 2022-12-12
SB1/US50 | my all files look like this | SB2/D1/T1 | 1. cnn_model.py (cnn architecture) | BK | 2022-12-13 | 2022-12-13
|  | SB2/D1/T2 | 2. dash.ui (dashboard inerface) | HJ | 2022-12-13 | 2022-12-13
|  | SB2/D1/T3 | 3. gust.ui (gesture interface) | AL | 2022-12-13 | 2022-12-13

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2022-10-25 | 5 | 0 | Tasks
2022-11-27 | 21 | 0
2022-12-04 | 10 | 2
2022-12-13 | 8 | 0
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Digital College>
SB1/US1 | As a Student I want discussed all about of project with my team | SB1/US1/T1 | our team member desided that on which platform we are going to implement our project | AL+BK+HJ | 2022-08-12 | 2022-09-22
|  | SB1/US1/T2 | A discussion were impactfull and all the eveluation part where identified by each one of us | AL+BK+HJ | 2022-09-24 | 2022-09-29
|  | SB1/US1/T3 | install the process regarding to this project | AL+BK+HJ | 2022-09-30 | 2022-09-30
|  | SB1/US1/T4 | Start working on Sign Language recognization system | AL+BK+HJ | 2022-10-01 | 2023-02-17
|  | SB1/US1/T5 | Install firstly Anaconda and Pycham IDE | BK | 2022-10-03 | 2022-10-03
|  | SB1/US1/T6 | Install Dev C++/C code editor And QTsdk | AL+HJ+BK | 2022-10-05 | 2022-10-05
SB1/US2 | As a Student I want discussed all about of project with my team | SB1/US2/T1 | Improved knowledge Regarding to this project firstly | AL+BK+HJ | 2022-10-10 | 2022-10-22
|  | SB1/US2/T2 | Discuss Among Other team member | AL+BK+HJ | 2022-10-25 | 2022-10-25
|  | SB1/US2/T3 | Finally working start in the project module Cnn model building | BK | 2022-11-01 | 2022-12-03
|  | SB1/US2/T4 | Creation of CNN architecture our first priority | BK | 2022-11-02 | 2022-12-03
|  | SB1/US2/T5 | view my result | BK | 2022-11-04 | 2022-11-04
SB1/US3 | we discused all rules of application working and library working | SB1/US3/T1 | Include The basic requirement like Python version 3 for code purpose | BK | 2022-11-05 | 2022-11-05
|  | SB1/US3/T2 | Include The basic requirement like Tensorflow for design the neural network arcitecture | BK | 2022-11-06 | 2022-11-06
|  | SB1/US3/T3 | Include The basic requirement like PIL library for image | BK | 2022-11-07 | 2022-11-07
|  | SB1/US3/T4 | Include The basic requirement like Keras for performing the task of image preprocessing | BK | 2022-11-07 | 2022-11-07
SB1/US6 | completed all the process of CNN training | SB2/D1/T1 | Include The basic requirement like Matplotlib library for image related operation and graph architectutre | BK+HJ | 2022-11-08 | 2022-11-08
|  |  | Creating the dataset for sign language classification | BK+HJ | 2022-11-13 | 2022-11-14
|  |  | Calculate threshold value | BK | 2022-11-15 | 2022-11-15
|  |  | Flipping the frame to prevent inverted image of captured frame | BK+AL | 2022-11-16 | 2022-11-16
|  |  | Display the threshold image | HJ | 2022-11-16 | 2022-11-16
SB1/US7 | completed all process of Data set creation by apply training | SB2/D1/T1 | Display the frame with segmented handed | BK | 2022-11-17 | 2022-11-17
|  | SB2/D1/T2 | Releasing the camera | AL | 2022-11-20 | 2022-11-20
|  | SB2/D1/T3 | Training CNN | BK | 2022-11-21 | 2022-11-21
|  | SB2/D1/T4 | Improved my performance and find best solution | BK | 2022-11-22 | 2022-11-22
SB1/US27 | Model Compilation | SB2/D1/T1 | Include The basic requirement like Python version 3 for code purpose | BK | 2022-11-23 | 2022-11-23
|  | SB2/D1/T2 | Predict the gesture | BK | 2022-11-24 | 2022-11-24
|  | SB2/D1/T3 | Release the camera | BK | 2022-11-24 | 2022-11-24
|  | SB2/D1/T4 | Package binding | BK | 2022-11-26 | 2022-11-26
|  | SB2/D1/T5 | Analysis of model archictecture in img view | BK | 2022-11-27 | 2022-11-27
SB1/US27 | start work on Gesture GUI interface | SB2/D1/T1 | Start learning about the GUI creation in python using PYqt5/qt6 | AL | 2022-11-08 | 2022-11-17
|  | SB2/D1/T2 | Start learning about the GUI creation in Qt sdk toolkit | AL | 2022-11-18 | 2022-11-24
|  | SB2/D1/T3 | Start working on creation of Gesture interface and create gesture.ui file | AL | 2022-11-25 | 2022-12-02
|  | SB2/D1/T4 | Analysis of xml archictecture in grid view | AL | 2022-12-04 | 2022-12-04
SB1/US150 | start work on dash GUI interface | SB2/D1/T1 | Start learning about the GUI creation in python using PYqt5/qt6 | HJ | 2022-11-08 | 2022-11-17
|  | SB2/D1/T2 | Start learning about the GUI creation in Qt sdk toolkit | HJ | 2022-11-18 | 2022-11-24
|  | SB2/D1/T3 | Start working on creation of Gesture interface and create dash.ui file | HJ | 2022-11-25 | 2022-12-06
|  | SB2/D1/T4 | Analysis of xml archictecture in grid view | HJ | 2022-12-07 | 2022-12-07
SB1/US28 | GUI integration and testing | SB2/D1/T1 | Convert the dash.ui file into py extension for find relation b/w py component | BK+HJ+AL | 2022-12-08 | 2022-12-08
|  | SB2/D1/T2 | Convert the gest.ui file into py extension for find relation b/w py component | BK+HJ+AL | 2022-12-09 | 2022-12-09
|  | SB2/D1/T3 | The project contains multiple files ; each file is discussed separately | BK+HJ+AL | 2022-12-12 | 2022-12-12
SB1/US50 | my all files look like this | SB2/D1/T1 | 1. cnn_model.py (cnn architecture) | BK | 2022-12-13 | 2022-12-13
|  | SB2/D1/T2 | 2. dash.ui (dashboard inerface) | HJ | 2022-12-13 | 2022-12-13
|  | SB2/D1/T3 | 3. gust.ui (gesture interface) | AL | 2022-12-13 | 2022-12-13

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2022-11-17 | 5 | 0 | Tasks
2022-11-24 | 90 | 110
2022-11-29 | 80 | 100
2022-12-10 | 66 | 65
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <Digital College>
| Start working on the gesture recognization module | SB2/D5/T4 | Install the basic requirement numpy for perform array related operation | BK | COMPLETED | 2023-01-19
SB1/US1 |  | SB2/D6/T1 | Install the basic requirement computervision library for perform camera related operation | BK
|  | SB2/D6/T2 | Bind the pretrained neural network file ASLmodel.h5 | BK
|  | SB2/D6/T3 | Actul working start on the function of imageprocessing | BK
| Start working on the gesture recognization module | SB2/D6/T4 | Working Start on to the pridict Function | BK | COMPLETED | 2023-01-24
|  | SB2/D6/T5 | Create the label for alphabetic signs | BK
SB2/US2 |  | SB2/D7/T1 | Hex bar working and its property value functionality | BK
|  | SB2/D7/T2 | In the end result is make in the form of recognize.py file | BK
|  | SB2/D7/T3 | Code testing for find any interpretation error | BK
| Start working on the gesture capture module | SB2/D7/T4 | Design and planning of the camera alignment and hand gestures | BK | COMPLETED | 2023-02-07
|  | SB2/D7/T5 | Creation the data set folder for testing and training | BK
SB3/US3 |  | SB2/D8/T1 | Start working on to the function image capture | BK
|  | SB2/D8/T2 | In the end result is make in the form of capture.py file | BK
| start working on gesture creation user interface | SB2/D8/T3 | Task planning and scheduing the task disscussion with Team mates | BK+HJ+AL | COMPLETED | 2023-02-16
|  | SB2/D8/T4 | Install the turbo C/C++ and QT5 SDK in the system | BK+HJ+AL
SB4/US4 |  | SB2/D2/T1 | Start working on to the create_gust.ui file | AL
|  | SB2/D2/T0 | Analyis the xml view of create_gust.ui file | AL
|  | SB2/D2/T2 | Conversion in .py /.ipny file for find relation and integration | AL+BK
| start working on single gesture creation user interface | SB2/D2/T3 | Task planning and scheduing the task disscussion with Team mates | BK+AL+HJ | COMPLETED | 2023-02-16
|  | SB2/D2/T4 | Install the turbo C/C++ and QT5 SDK in the system | HJ
SB5/US5 |  | SB2/D2/T5 | Start working on to the scan_single.ui file | HJ
|  | SB2/D3/T1 | Analyis the xml grid view of scan_single.ui file | HJ
|  | SB2/D3/T2 | Conversion in .py /.ipny file for find relation and integration | HJ+BK
| all files look like this | SB2/D3/T3 | 1. cnn_model.py | BK | COMPLETED | 2023-02-20
SB6/US6 |  | SB2/D3/T4 | 2.capture.py | BK
|  | SB2/D4/T1 | 3.recognize.py | BK
|  | SB2/D4/T2 | 4.dash.ui | HJ
|  | SB2/D4/T3 | 5.export.ui | AL
SB7/US7 | merge all algorithms through connectivity | SB2/D4/T4 | 6.create_gust.ui | AL | COMPLETED | 2023-02-20
|  | SB2/D4/T5 | 7.scan_single.ui | HJ
SB2/D5/T1
SB2/D5/T2

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2023-01-19 | 4 | 0 | Tasks
2023-01-24 | 5 | 0
2023-02-07 | 4 | 0
2023-02-16 | 10 | 8
2023-02-20 | 5 | 5
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Digital College>
SB1/US1 | As a Student I want discussed all about of project with my team | SB2/D1/T1 | our team member desided that on which platform we are going to implement our project | BK + AL +HJ | COMPLETED | 2023-02-20
|  | SB2/D1/T2 | A discussion were impactfull and all the eveluation part where identified by each one of us | BK + AL +HJ | COMPLETED | 2023-02-20
|  | SB2/D1/T1 | install the process regarding to this project | BK | COMPLETED | 2023-02-20
SB1/US1 | start working on dash board backend file | SB2/D1/T1 | Create the conda environment | BK | COMPLETED | 2023-02-21
|  | SB2/D1/T1 | Start working on dash.py file | BK | COMPLETED | 2023-02-21
|  | SB2/D1/T1 | Install the dependencies | BK | COMPLETED | 2023-02-21
|  | SB2/D1/T1 | Work start on define filesearch() method | BK | COMPLETED | 2023-02-22
|  | SB2/D1/T1 | Work start on define load_images_from_folder() method | BK | COMPLETED | 2023-02-22
SB1/US1 | start working on dash board backend file | SB2/D1/T3 | Start wotking on toggle_imagesfwd() function | BK | COMPLETED | 2023-02-22
|  | SB2/D1/T3 | Start working on toggle_imagesrev() function | BK | COMPLETED | 2023-02-23
|  | SB2/D1/T3 | View My Result | BK+AL+HJ | COMPLETED | 2023-02-25
|  | SB2/D1/T3 | Start working on toggle_imagesrev() function | BK | COMPLETED
SB1/US1 | Start working on scan export file | SB2/D1/T3 | Task planning and scheduing the task disscussion with Team mates | BK+AL+HJ | COMPLETED | 2023-02-25
|  | SB2/D1/T3 | Install the turbo C/C++ and QT5 SDK in the system | AL+HJ | COMPLETED | 2023-02-26
|  | SB2/D1/T3 | Start working on to the scan_sent.ui file | AL+HJ | COMPLETED | 2023-02-26
|  | SB2/D1/T3 | Analyis the xml grid view of scan_sent.ui file | AL+HJ | COMPLETED | 2023-03-01
|  | SB2/D1/T1 | Conversion in .py /.ipny file for find relation and integration | BK+HJ | COMPLETED | 2023-03-01
SB1/US1 | Continue working on dash board backend file | SB2/D1/T1 | Start wotking on openimg() function | BK | COMPLETED | 2023-03-02
|  | SB2/D1/T1 | Start wotking on removeFile() function | BK | COMPLETED | 2023-03-02
|  | SB2/D1/T2 | Start wotking on clearfunc() function | BK | COMPLETED | 2023-03-02
|  | SB2/D1/T1 | Start wotking on predictor() function | BK | COMPLETED | 2023-03-06
SB1/US1 | Continue working on dash board backend file | SB2/D1/T2 | Start wotking on Dashboard() function | BK+HJ | COMPLETED | 2023-03-09
|  | SB2/D1/T3 | Start wotking on createGest() function | BK+HJ+AL | COMPLETED | 2023-03-10
|  | SB2/D1/T1 | Start wotking on exportFile() function | BK+HJ+AL | COMPLETED | 2023-03-12
|  | SB2/D1/T2 | Start wotking on on_click() function | BK | COMPLETED | 2023-03-13
|  | SB2/D1/T1 | Start wotking on gestureViewer() function | BK+HJ | COMPLETED | 2023-03-13
SB1/US1 | Continue working on dash board backend file | SB2/D1/T3 | Start wotking on scanSent() function | BK | COMPLETED | 2023-03-14
|  | SB2/D1/T3 | Start working on scanSingle() function | BK+HJ+AL | COMPLETED | 2023-03-14
|  | SB2/D1/T2 | Integration of all files | BK+HJ+AL | COMPLETED | 2023-03-15
|  | SB2/D1/T1 | The project contains multiple files ; each file is discussed separately | BK+HJ+AL | COMPLETED | 2023-03-15
|  | SB2/D1/T2 | After all the above thing are complete | BK+HJ+AL | IN PROGRESS | 2023-04-22
SB1/US1 |  | SB2/D1/T1 | Finally Output are provided | BK+HJ+AL | IN PROGRESS | 2023-04-25
SB2/D1/T3
SB2/D1/T2
SB2/D1/T1

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2023-01-31 | 177 | 190 | Tasks
2023-02-07 | 110 | 150
2023-02-14 | 80 | 100
2023-02-21 | 25 | 16
2023-02-28 | 15 | 15
2023-02-05 | 0 | 0
0
Days